## Table 1
NAME: Laxman Shinde CLASS: SYMCA DIV: A ROLLNO: 52062 BATCH : S3
|  |  | Severity |  |  | Status
|  | Critical |  |  | New
|  | Major |  |  | In Progress
|  | Minor |  |  | Resolved
Defect ID | Date Reported | Reported By | Defect Description | Severity | Action | Assigned To | Resolved Date |  | Status
D001 | 2024-09-15 | User123 | Cart not updating correctly | Major In Progress |  | Dev1 | 2024-09-20 |  | Needs urgent attention
Payment
D002 | 2024-09-16 | User456 | gateway | Critical | New | Dev2 | 2024-09-18 |  | Occurs intermittently
timeout
D003 | 2024-09-17 | User789 | Product image not loading | Minor Resolved |  | Dev3 | 2024-09-19 | 2024-09-18 | Fixed in the latest build
D004 D005 D006 | 9/18/2024 9/19/2024 9/20/2024 | User101 User202 User303 | Incorrect pricing displayed Search function not working User profile not saving changes | Major | New | Dev4 Dev5 Dev1 | 9/22/2024 9/21/2024 9/25/2024 |  | Check backend data Affects user experience Investigating
|  |  |  | Critical | In Progress
|  |  |  | Major | New
D007 D008 | 9/20/2024 9/21/2024 | User404 User505 | Order confirmation email not sent Discount code not applying | Minor Resolved |  | Dev2 Dev3 | 9/21/2024 9/24/2024 |  | Issue with email server Verify discount logic
|  |  |  | Major | New
D009 | 2024-09-22 | User606 | Mobile view issues | Minor | In Progress | Dev4 | 2024-09-26 |  | Responsive design fix
D010 | 0 | User707 | Checkout page freezing | Critical | New | Dev5 | 2024-09-25 |  | High impact on sales
Formulas:
Date Reported = [Date Reported]:N24

## Sheet1
NAME: LAXMAN SHINDE CLASS: SYMCA DIV: A ROLLNO: 52062 BATCH : S3
|  |  |  | Severity |  |  | Status
|  |  | Critical |  |  | New
|  |  | Major |  |  | In Progress
|  |  | Minor |  |  | Resolved
Defect ID | Date Reported | Reported By | Defect Description | Severity | Status | Assigned To | Target Fix Date | Actual Fix Date | Comments
D001 D002 | 9/15/2024 9/16/2024 | User123 User456 | App crashes on login Balance not updating in real-time | Critical | In Progress | Dev1 Dev2 | 9/20/2024 9/18/2024 |  | Needs urgent attention Verify API response
|  |  |  | Major | New
D003 D004 | 9/17/2024 9/18/2024 | User789 User101 | Transaction history not loading Incorrect PIN error message | Major | Resolved | Dev3 Dev4 | 9/19/2024 9/22/2024 | 2024-09-18 | Fixed in latest update Adjust message text
|  |  |  | Minor | New
D005 | 2024-09-19 | User202 | App freezes on making a payment | Critical | In Progress | Dev5 | 2024-09-21 |  | High impact on users
D006 D007 D008 | 9/20/2024 9/20/2024 9/21/2024 | User303 User404 User505 | Notifications not being received Face ID not working for login App layout issues on older devices | Major Major | New | Dev1 Dev2 Dev3 | 9/25/2024 9/21/2024 9/24/2024 | 2024-09-20 | Check push notification settings Compatibility issue Test on various devices
Resolved
|  |  |  | Minor | New
D009 | 2024-09-22 | User606 | Unable to edit profile information | Major | In Progress | Dev4 | 2024-09-26 |  | Needs immediate attention
Error in
D010 | 2024-09-23 | User707 | generating account | Critical | New | Dev5 | 2024-09-25 |  | Validate report generation process
statement

## Sheet2
NAME: LAXMAN SHINDE CLASS: SYMCA DIV: A ROLLNO: 52062 BATCH : S3
DEFECT REPORT
|  |  |  | User Impact | Business impact
Status | Count |  | 1-Critical | #REF! | #REF!
1-New | 1 |  | 2-High | 2 | 2
2-Open | 4 |  | 3-Medium | 3 | 0
3-Closed | 0 |  | 4-Low | 0 | 2
TOTALS | 5 |  |  | #REF! | #REF!
Defect ID | Detected Date | Customer ref | Status | H/M/L User impact | H/M/L Business impact | Summary | Reported by | Defect / issue description | Environment | Customer facing update | Internal Update | Assigned to
1 | 2021-01-31 | 438 | 1-New | 2-High | 2-High | CRM connector: Email address gives error when saving. | Customer test team | Search for a relation (with email address) in the connector. Select relation. Confirm your choice. Enter empty fields. Click save and close Expected: Relation will be stored and closed Observed behavior: Error message | QA | With Engineer for review. | Check there isn't a conflict between test data email addresses and live addresses imported via the connector. | Engineer
2 | 2021-01-15 | 441 | 2-Open | 3-Medium | 4-Low | Need button to clear all fields. | Customer test team | The connector tab contains 8 search fields. I'm missing a button here to clear all fields for a new search. | Dev | New requirement. Workaround is to manually clear the fields. Engineer is assessing the effort. | Likely to be several days work. Will provide an estimate of effort to the customer. | Engineer & PM
3 | 2020-12-30 | 442 | 2-Open | 3-Medium | 2-High | Nationality is not given correctly. | Customer test team | Insured person (policy member) - nationality is not coming through connector. | QA | With Engineer for review. | Nationality data is in data import so should be coming through. | Engineer
4 | 2021-01-08 | 445 | 2-Open | 2-High | 1-Critical | Insured view shows 0 in policy tab. | Customer test team | Connector: Customer view Insured gives result 0 at Policy tab. | Dev | Related to “Link between Policy owner and Policy member not available”. | Looking at the XML data it seems that this member is not a policy owner, so the policy data is not in the XML. We need to see if we can add these memberships (as part of a change request). | Engineer
5 | 2021-01-11 | 450 | 2-Open | 3-Medium | 4-Low | Change search for Group Contract. | Customer project team | Search for Group Contract needs to return associated organisation record. At the moment the reference no. is returned. | QA | New requirement. Consider for future phase. | Raising a change request. Work around - show the organisation under group contract and drill down on the organisation for details. | PM & Engineer for LOE